## Overview
Roadwatch Vision Recorder — Current Coverage Status
Snapshot prepared 15 July 2026 from the current repository code, README, and commit history
Metric | Current count | Current position | Meaning | Priority
Implemented workstreams | 18 | Implemented in codebase | Feature exists in the current repository. | Maintain
Core AI capabilities | 4 | Field testing in progress | Vehicle, mobile, recorder, media, and location behaviour require practical validation. | High
Operational dashboard areas | 9 | Integration testing pending | Cloud services and optional API require configured credentials or external systems. | Medium
Optional integration connectors | 3 | Security/configuration review | Secrets, permissions, privacy settings, and deployment configuration require final review. | High
Latest recorded development activity | 2026-07-06
Use the Coverage Register as the detailed record of what has been covered. The verification column intentionally marks tests that are still needed; it does not mean the feature is absent.

## Coverage Register
Coverage Register — Implemented Work to Date
Status reflects code and documentation evidence as at 15 July 2026
Area | Covered functionality | Codebase status | Verification / current state | Primary evidence
Live recording | OpenCV webcam capture, in-page preview, start/stop controls, recording timer, storage status, and background capture thread. | Implemented | Field testing in progress | streamlit_app.py; core/opencv_recorder.py
Video files | Original high-resolution WebM recordings, legacy MP4 compatibility, processed-video fallback, and local metadata per recording. | Implemented | Playback and compatibility testing in progress | services/video_service.py; core/video_io.py
AI object detection | YOLOv8 detection for people, vehicles, and other COCO objects with configurable image size and confidence. | Implemented | Validate against real driving footage | core/detector.py; core/vision_pipeline.py
Object tracking | Deep SORT tracking IDs and captured-object summaries for each recording. | Implemented | Validate tracking stability in vehicle tests | core/tracker.py; core/vision_pipeline.py
Movement analysis | Movement detection and movement-event metadata captured against video IDs. | Implemented | Validate thresholds in varied conditions | core/movement.py; services/detection_log_service.py
OCR / plate scanning | Optional EasyOCR plate scanning with plate text, confidence, and bounding-box metadata. | Implemented | Validate plate accuracy and OCR intervals | core/ocr.py; core/vision_pipeline.py
Video post-processing | Full post-recording AI pass that produces annotated processed WebM video and rebuilds detection metadata. | Implemented | FFmpeg/MoviePy compatibility testing in progress | services/video_processing_service.py
Evidence library | Search, filters, original/processed selector, video playback, detection timeline, object table, and missing-file diagnostics. | Implemented | Validate against a larger recording set | streamlit_app.py
Incidents | Generated and manual incidents; filters by severity, type, and status; review and dismissal workflow. | Implemented | End-to-end workflow testing pending | services/incident_service.py; streamlit_app.py
Stolen vehicle watchlist | Local reported-vehicle records, plate search, OCR matching, and high-severity incident creation for potential matches. | Implemented | Validate matching and report workflow | services/stolen_vehicle_service.py
GPS history | Local/mock GPS history, live location-tracking service, speed/location status, and video-linked GPS points. | Implemented | Validate active GPS in vehicle/mobile tests | services/gps_service.py; streamlit_app.py
Emergency contacts & SOS | Local contact management, active-contact count, SOS action, and notification dispatch integration. | Implemented | Test with configured notification provider | services/contact_service.py; services/notification_service.py
Vehicle profile | Local vehicle and driver/fleet profile for reporting and future exports. | Implemented | Data-entry validation pending | services/vehicle_profile_service.py
Analytics & reports | Aggregate recording, incident, detection, plate, movement, duration, and processing-error metrics with dashboard charts. | Implemented | Validate totals with representative data | services/report_service.py; streamlit_app.py
Settings & privacy | Camera, AI, storage, sync/API, notification settings, environment loading, and privacy-consent gate. | Implemented | Security/configuration review pending | streamlit_app.py; settings.json; .env.example
Authentication | Local admin authentication and development credential checks. | Implemented | Security review pending | services/auth_service.py
Cloud/sync connectors | Optional Supabase upload/public URLs, Firebase document sync, upload queue, and external API sync service. | Implemented (optional configuration) | Requires service credentials and integration testing | services/supabase_service.py; services/firebase_service.py; services/sync_service.py
Optional API | FastAPI application for future integration with an existing dashcam platform. | Implemented | Integration testing pending | api_app.py

## Development History
Development History — Recorded Milestones
Derived from repository commit dates and messages
Date | Milestone | Recorded activity
2025-07-19 | Project repository started | Initial project files and documentation committed.
2025-08-23 | Documentation update | Repository documentation updated.
2026-05-12 | Dashboard/service work added | Current Streamlit application and supporting services added to repository history.
2026-06-11 | Code preservation checkpoint | Project code saved before further changes.
2026-06-22 | Vehicle & mobile testing | Vehicle testing and mobile testing work recorded.
2026-06-24 | Contributor setup | Project updated to make contributor onboarding easier.
2026-07-01 | WebM & active location tracking | MP4-to-WebM work and active location tracking recorded; testing identified as next step.
2026-07-03 | Webcam recorder fixes | Further recorder fixes recorded.
2026-07-06 | MoviePy / FFmpeg work | MoviePy integration and FFmpeg work recorded; saving information verified.