## Project Schedule
Roadwatch Vision Recorder — Project Timeline
Accelerated three-month schedule; planning baseline: 14 July 2026 ¦ target completion: 14 October 2026
Phase | Milestone / Workstream | Scope | Start Date | Target Completion | Duration (days) | Status | Notes
1 | Project foundation & initial prototype | Set up object detection, tracking, video I/O, and the initial repository. | 2025-07-19 | 2025-08-22 | 35 | Complete | Historical milestone
2 | Core recorder & detection pipeline | Build webcam/dashcam recording, YOLO detection, movement analysis, OCR, and saved-video workflow. | 2025-08-23 | 2026-05-11 | 262 | Complete | Historical milestone
3 | Dashboard & service integration | Develop Streamlit dashboard plus incident, vehicle, reporting, storage, and notification services. | 2026-05-12 | 2026-06-10 | 30 | Complete | Historical milestone
4 | Video compatibility & GPS tracking | Integrate MoviePy/FFmpeg, improve MP4/WebM handling, and enable active location tracking. | 2026-06-11 | 2026-07-06 | 26 | Complete | Historical milestone
5 | System & mobile testing | Complete vehicle/mobile testing, webcam recorder reliability checks, and media persistence tests. | 2026-07-07 | 2026-07-24 | 18 | In Progress | Current workstream — finish by 24 Jul
6 | Defect resolution & performance tuning | Resolve test findings; tune recording stability, inference speed, playback, and location accuracy. | 2026-07-25 | 2026-08-07 | 14 | Not Started | Depends on Phase 5
7 | Feature hardening | Finalize critical incidents, stolen-vehicle checks, analytics, exports, and error handling. | 2026-08-08 | 2026-08-21 | 14 | Not Started | Critical features only
8 | Security & data review | Review authentication, secrets, access controls, retention, backup, and privacy settings. | 2026-08-22 | 2026-08-28 | 7 | Not Started | Run in parallel where possible
9 | User acceptance testing | Run end-to-end driving scenarios, capture acceptance feedback, and fix release-blocking issues. | 2026-08-29 | 2026-09-11 | 14 | Not Started | Depends on Phases 7–8
10 | Release preparation | Complete essential documentation, installation steps, release notes, and deployment checklist. | 2026-09-12 | 2026-09-23 | 12 | Not Started | Keep documentation release-focused
11 | Pilot deployment & monitoring | Deploy a controlled pilot, monitor priority errors, and apply only release-blocking fixes. | 2026-09-24 | 2026-10-07 | 14 | Not Started | Depends on Phase 10
12 | Production release & closeout | Publish production release, hand over essential documentation, and close the project. | 2026-10-08 | 2026-10-14 | 7 | Not Started | Hard deadline: 14 Oct 2026
Project start | Planning baseline | Target completion | Total timeline (days) | Remaining from baseline (days)
2025-07-19 | 2026-07-14 | 2026-10-14 | 453 | 92

## Planning Notes
Planning Notes & Assumptions
Item | Draft assumption
Historical start | 19 July 2025, based on the earliest repository commit.
Planning baseline | 14 July 2026, the date this draft was prepared.
Current focus | Vehicle/mobile testing, recorder reliability, media handling, and active location tracking. The remaining plan is compressed to three months.
Target completion | 14 October 2026, a fixed three-month deadline from the planning baseline. Scope must remain focused on release-critical work.
How to use | Update Status, dates, and notes weekly. Escalate any item marked At Risk immediately to protect the fixed completion date.
Status | Meaning
Not Started | Scheduled work has not begun.
In Progress | Active work is underway.
At Risk | The target date may slip without corrective action.